## Sheet1
sprint (1)
ID | task Name | weight % | planned time
1 | create sign up page | 25% | 2 days
2 | create sign in page | 15% | 1 days
3 | create Reset password option | 10% | 1 days
4 | save data in database with testing it | 25% | 2 days
5 | create APIs | 15% | 2 days
6 | test the final code with all modification | 10% | 2 days

## Sheet2
days | Goals | done | planned | actual
sun | 15% | 15% | 85% | 85%
Mon | 10% | 15% | 75% | 70%
Tues | 15% | 12% | 60% | 58%
wedn | 10% | 11% | 50% | 47%
thurs | 13% | 10% | 37% | 37%
sun | 12% | 9% | 25% | 28%
Mon | 8% | 9% | 17% | 19%
Tues | 7% | 9% | 10% | 10%
wedn | 5% | 7% | 5% | 7%
thurs | 5% | 3% | 5% | 5%